## Target IQ
[Project Title]
Target monitoring (Actual vs planned)
[10 empty] | Quarter 1 | [6 empty] | Quarter 2 | [6 empty] | Quarter 3
Outcome | Indicator | Target population | Reference value | Target value project | Total reached vs target | Target T1 | month 1 | month 2 | month 3 | Total | % reached Q1 | Gap explanation | Target T1 | month 1 | month 2 | month 3 | Total | % reached Q1 | Gap explanation | Target T1 | month 1 | month 2 | month 3 | Total | % reached Q1 | Gap explanation
Objective "x"
Indicator O1
Indicator O2
Final Result I "y"
Indicator I.1
Indicator I.2
Indicator I.3
Intermediate Result I.1
Indicator I.1.a
Indicator I.1.b
Activity I.1.1
Indicator (output) | # of children receiving structured PSS support from Tdh | NNA Camp X - Y identified by X or referred by Z | 0 | 200 | 93% | 50 | 0 | 4 | 21 | 34 | 68% | Month 1 : preparation phase, staff recruitment, additional staff training | 80 | 29 | 36 | 27 | 92 | 115% | Service Promotion and awareness raising. Improved work with local child protection committees | 70 | 33 | 25 | 2 | 60 | 85.71% | Phase out Quarter 3 - funding gap
Indicator (output)
Activity I.1.2
Indicator
Indicator
Intermediate Result I.2
Indicator I.2.a
Indicator I.2.b
Activity I.2.1
Indicator (output)
Indicator (output)
Activity I.2.2
Indicator
Indicator
Final Result 2 "y"
Indicator 2.1
Indicator 2.2
Indicator 2.3
Intermediate Result 2.1
Indicator 2.1.a
Indicator 2.1.b
Activity 2.1.1
Indicator
Indicator
Activity 2.1.2
Indicator
Indicator
Intermediate Result 2.2
Indicator 2.2.a
Indicator 2.2.b
Activity 2.2.1
Indicator
Indicator
Activity 2.2.2
Indicator
Indicator